## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Green
Project: Green
Crypto2.0WeLoveAds
Lucas Winger, Cheryn Lindsay, Joseph DeJong
Project start date: | 2025-03-09 | [10 empty] | Scrolling increment: | [5 empty] | 13
Milestone marker: | 1 | 1 |  |  | March | [13 empty] | April | [27 empty] | May
 | time axis 2025-03-22 to 2025-05-16
Milestone description | Assigned to | Progress | Start | Days | time axis 2025-03-22 to 2025-05-16
Milestone 4 (frontend) | bar: 2025-03-22
Create Index/Schedule Screens | Lucas | 100% | 2025-03-09 | 3
Create Search / Settings Screens | Cheryn | 100% | 2025-03-16 | 4
Creat Add / Edit Screens | Joseph | 100% | 2025-03-15 | 3
Update XML files to appear while running | Joseph+Lucas | 100% | 2025-03-23 | 4
Work On Gantt Chart | Joseph+Cheryn | 100% | 2025-03-18 | 1
Create navigation between pages | Cheryn+Lucas | 20% | 2025-03-20 | 7
Refactor layout files | Cheryn | 10% | 2025-03-18 | 4
Milesone 5 (Start backend) | bar: 2025-03-29
Implement Google Calender | Lucas | 60% | 2025-03-28 | 13
Figure out Permissions | Cheryn | 0% | 2025-03-28 | 4
Redirect to Map Apps | Joseph | 0% | 2025-03-28 | 9
Start Notifications | Joseph | 0% | 2025-03-28 | 11
Dark/Light Mode | Cheryn | 0% | 2025-03-28 | 7
Color Options | Lucas | 0% | 2025-03-28 | 24
Milestone 6 (Implement Database) | bar: 2025-04-12
Create Event Table | Lucas | 0% | 2025-04-11 | 4
Create Reminder Table | Lucas | 0% | 2025-04-11 | 5
Create database connection | Cheryn | 0% | 2025-04-11 | 14
Categories | Cheryn | 0% | 2025-04-11 | 6
Storing events | Joseph | 0% | 2025-04-11 | 15
retrieving events | Joseph | 0% | 2025-04-11 | 15
MileStone 7 (Present / final touchup) | bar: 2025-04-21
Ensure bug free project | Joseph+Lucas | 0% | 2025-04-20 | 15
Finish Backend/Database | Joseph+Cheryn | 0% | 2025-04-20 | 4
Create presentation | Cheryn+Lucas | 0% | 2025-04-20 | 5
To add more data, Insert new rows ABOVE this one